Age Friendly City Steering Group

Wednesday 7th August 2013

King’s House

Meeting Notes

Present:

Annie Alexander (AA)		Public Health Programme Manager (Chair)

Anna Richmond (AR)		Lifelines

Sarah Tighe-Ford (STF)	BHCC

Keith Beadle (KB)		The Fed

Mike Bojczuk (MBO)		Older People’s Council

Marian Barnes (MBA)		University of Brighton

Jessica Sumner (JS)		Age UK

Jane Macdonald (JM)		BHCC

Becky Woodiwiss (BW)	BHCC

Carolyn Phelps (CP)		DWP

Liz Whitehead (LW)		Fabrica

Ellie Katsourides (EK)		Public Health Team Admin (minutes)

Apologies:

Michelle Pooley (MP)		BHCC

Alzheimers Society

Jane Lodge			CCG

| Item |  | Action |
| --- | --- | --- |
| 1. | Welcome, introductions and apologies AA welcomed all to the meeting and apologies received were as noted above. |  |
| 2. 2.1 2.2 2.3 2.4 | Notes from the previous meeting The notes from the previous meeting were approved with the following Actions and Matters Arising: 2.2 - c/f - AA to talk to Keith Beadle at The Fed about the work they are doing on Transport. Tracey Maitland advised it is part of the ‘To and From’ project and noted that The Fed is running an event on 17th July at the St. John’s Centre and café, targeted at new and existing volunteers. Some volunteering organisations will also be there. TM to send AA details of the event. 2.5 – c/f - AA advised that she went to a very interesting presentation by David Golding (DG), BHCC Senior Analysis & Research Officer information analyst, on the Census 2011 information which she plans to follow up on. Some of the population figures are different to the mid year projections so it is very important that everyone has the up-to-date data. The Census information is coming out in dribs and drabs and DG has done some useful analysis of what we have so far. JS enquired whether we can see it as it is not yet on BHLIS. AA will contact DG and ask for a copy of his presentation and then send it on to this group. The group discussed the possibility of asking him to do some work specifically around the older population and then asking him to attend the next meeting. Lottery Bid – AA advised that we are through to the next stage and are down to 1 of 32 which will then be whittled down to 20. People’s Day – AA enquired whether the event had been written up at all. AR advised that she will look into this as she is sure it had been, and she will distribute the notes. She had attended meetings and been asked to give feedback. Key notes had been that the promotion was started too late and that some people had had difficulties in attending. Next year’s event will be tendered and STF advised this is being led by Emma McDermott. AA to liaise with Emma. | AA follow up with TM/KB AA AR AA |
| 3. 3.1 | AFC Progress City Assessment and Membership AA enquired as to how the group felt about its current membership and whether some key players in older people services were not currently included. AA asked the group who else they thought she be invited to attend e.g. Impact; NHS; NCS. AA has spoken to the CCG to try and identify someone from their end to attend in future but is having difficulties in getting commitment. MB commented that she felt that institutional partners should sign up to the group and she will draw up a list of ideas/contacts such as Brighton University Vice-Chancellor, for AA to contact and ask for some commitment. JS added that it would be useful to have a timeline in order to encourage buy in and to provide clarity with the goals. MB proposed a tie in with Ageing Better where there is existing funding in order to attract people to it. AR proposed a city wide strategy meeting to come up with a plan on how to engage others to cover the bid to ensure the AFC is not lost. External attendees could then be invited to attend and provide advice where appropriate. AA noted that the strategy comes out of the assessment according to the WHO process, so maybe the timeline should be based around that. KB queried at what point to older people get to input their views on the strategy and assessment as we need to engage with the OP community about what issues need to be addressed. JS suggested that somebody from The Forum could be included and she could clarify with them what they see their role as being. The group discussed the possibility of doing a baseline survey before and after, perhaps using focus groups and key questions. MBO proposed a questionnaire could be used and could be distributed at the OP Day. LW flagged up that culture does not seem to come up in the assessment and is an area Brighton & Hove is strong in. She advised that she would be happy to represent the Arts in this group and suggested a network of Arts providers who could meet separately and feed in to this group. LW proposed that the Libraries and Museum services should also be included. CP enquired whether AA was a member of the Age Action Alliance and if not, suggested that it would be a good idea. AA is on their circulation list. KB noted that we need to be clear on the messages going out and to raise awareness of what we are doing and proposed that we think about a possible Comms Strategy. We need to link in to the agendas of other organisations and groups. AA noted that she was wary of this group becoming too big. The group discussed theming meetings around the domains and having themed discussions where they can invite relevant organisations, individuals or LSP groups to contribute. The group agreed this was a good idea as it might help get appropriate attendance and help identify some priorities. The group also discussed how best to engage older people in the process - it was suggested that the discussions with OP can take place within existing focus groups or at an event where people choose which topics they want to feed in on. We need to be aware of which funded groups are working with OP already and try to ensure engagement across the city. All forms of engagement need to be considered. MB has come up with some indicators which could be used as a basis for framing questions to OP. MB noted that we also need to be aware of what the domains in the assessment do not cover. The group discussed how best to proceed and which domain to start with. JS proposed Transportation to start with as it underpins many other domains. STF suggested broadening it to a more generic topics such as ‘out and about’. AA proposed a small group of herself, JS, KB and MB meet to pin down a theme and how to get the process started which they could then send round to the group for comments. EK to arrange. | MB/AA AA/JS/KB MB EK |
| 4. 4.1 4.2 4.3 | Draft TORs Role and Function - Wording of the first sentence to be amended with the removal of: ’for relevant professionals to come together’. Additional bullet point: Embed AFC to other key work strands. Membership - The group looked at the TORs in light of the discussion and agreed to remove named people from the membership list and only list the organisations. These to now include NCS, Impetus, Impact Initiatives, Pension Service, and Police. It was agreed that apart from the main membership list, there would be a much wider circulation list for people’s info. It was agreed that Steering Group members will not only represent their organisation, but will also represent their sector and will be responsible for passing on key messages and reporting back to their sector as appropriate. The Learning Partnership and The Carer’s Centre to be added to the circulation list. AA to look into whether the LSP is the right route. Other wider equalities groups such as BMECP and the LGBT Switchboard to be considered for the wider circulation list. Administration – Clarify the wording of 6.1 and amend email address in 6.2 to include GSX. | AA AA AA All AA |
| 5. 5.1 5.2 | AFC Progress AFC UK Shadow Network AA advised that here has been a series of enquiry visits on Arts and Older People and she had visited Stoke for one of these last month. It had struck her how well we are doing in Brighton & Hove. She will look at the notes and distribute them to the group. BW will be attending the next Steering Group meeting in October on AA’s behalf so if anybody would like anything raised at that meeting they should contact BW directly. The group discussed the possibility of a visit to Brighton & Hove and what it could be on. It was proposed that we either do it on something we do well or on something we are struggling with one idea suggested was consultation and engagement of Older People. BW will find out more about what a visit here would entail at the October SG meeting and feed back on the processes involved Indicators MB talked through the indicators that had been suggested by the well-being research undertaken by the University and Age UK. The research looked at what does well-being mean for OP. It relates to relationships and capacity to sustain them. How they experience the place they live effects relationships. The indicators could be used to design a bigger survey/study though this would require resources, particularly in order to get a baseline, which would be useful. The group was asked to look at the indicators and feed in any comments to MB. AA will look to see how these indicators map to the domains. | AA ALL BW All AA |
| 6. | Older People’s Day AA advised that this year Public Health have some money to help celebrate Older People’s Day. They have put out an Invitation to Quote and have had some interest. They are now finalising who they will invite to take this forward and will let people know in the next couple of days. At the moment AA does not know if there will be the money to do something similar next year and will let people know once the situation becomes clear. KB noted that funding may become available through other public sector organisations in future e.g. The Police. |  |
| 7. | AOB - JM advised that B&H has been awarded £980k from the Department of Health to be spent on Dementia capital projects by February 2014. This money will go to GP surgeries, day services, care homes and a number of wards at RSCH and Mill View. The money is for Dementia environments, both diagnosed and undiagnosed. |  |
|  | Dates of Future Meetings Future meetings will take place at King’s House on: Wednesday 9th October, 2 – 4pm Wednesday 4th December, 10am – 12 pm Wednesday 5th February, 10am – 12 pm Wednesday 9th April, 10am – 12 pm |  |